## Solution & Work Assignment
Sr No | Solution Description | Type | Status | Description | Owner | Target Date |  |  |  | Solution
1 | Inbound IVR Calling | Capability | Closed | Demo Available | Karan |  |  |  |  | Capability
2 | Amazon Connect integration with Salesforce | Capability | Closed | Demo Available | Karan |  |  |  |  | Demo
3 | Amazon Lex integration with Genesys Cloud | Capability | Closed | Demo Available | Karan
4 | Amazon Lex integration with Alexa | Capability | Closed | Demo Available | Karan
5 | Email Campaign - Maze | Demo | Closed | Demo Available | Mohan
6 | SMS Campaign - Maze | Demo | Closed | Demo Available | Mohan
7 | Transactional email and SMS notification | Capability | Closed | Demo Available | Mohan
8 | Voice Virtual Assistance | Capability | Closed | Demo Available | Karan
9 | Chat Virtual Assistance | Demo | Closed | Demo Available | Shubhada
10 | Multilingual Chatbot | Demo | Closed | Demo Available | Shubhada
11 | Bot Supervised training | Solution | Closed | Demo Available | Mohan/Karan
12 | Bot supervised Testing | Solution | Closed | Demo Available | Mohan/Karan
13 | Post Call Surveys | Solution | Closed | Demo Available | Rajiya
14 | Amazon Connect Dashboards | Capability | Closed | Demo Available | Rajiya
15 | Lex Dashboards | Capability | Closed | Demo Available | Rajiya
16 | Outbound Campaign | Solution | In Progress | Configuration is in progress | Rajiya
17 | Authentication via Voice ID | Demo | Closed | Demo Available | Karan
18 | Chatbot transfer to Live Agent (Sparc) | Demo | Closed | Demo Available | Karan & Shubhada
19 | Agent to agent call transfer | Capability | Closed | Demo Available | Mohan | 2023-03-31
20 | Agent Assist with suggestion box and automation of chat response with pre configured response messages | Solution | Closed | Hosting Remaining | Shubhada / Rajiya | 2023-03-31
21 | Amazon Connect integration with Salesforce with transcription and pii redaction | Demo | Closed | Demo Available | Karan
22 | Fraud Detection for inbound calls with Machine Learning | Solution | Closed | Demo Available | Rajiya | 2023-03-20
23 | Keywords based multilingual search display functionality using Amazon opensearch and amazon translation | Solution | In Progress | Hosting remaining | Shubhada
24 | Create Amazon connect flow uisng APIs | Solution | Closed | Demo Available | Rajiya
25 | Dynamic Prompts in Connect flow coming from Dynamo DB | Solution | Closed | Demo Available | Mohan
26 | Network Bot Solution and Approach | Demo | Closed | Demo Available | Shubhada/Rajiya | 2023-04-05
27 | Estimated wait time in queue if agent unavailable to take calls | Capability | Closed | Demo available | Mohan | 2023-03-31
28 | Facebook Virtual Assistance | Capability | On Hold | Configuration is in progress | Shubhada/Karan | 2023-03-31
29 | Whats App Virtual Assistance | Capability | Not Started | Re-work to be done | Shubhada
30 | Real time translation & Transcription | Solution | Closed | Configuration is in progress | Mohan | 2023-03-31
31 | LiveChat Framework & Solution |  | In Progress | Design is in progress | Sagar | 2023-03-31
32 | Amazon Connect CI/CD Connect Flow LEX automation | Solution | Completed | Demo Available | Karan | 2023-04-21
33 | Amazon Connect CI/CD UI |  | Completed | Configuration is in progress | Prathyusha | 2023-04-21
34 | Video Calling | Solution | Hold | Yet to start | Mohan | 2023-02-17
35 | Amazon Connect Chat Wisdom and automated Evaluation form | Capability | Completed | Demo Available | Mohan | 2023-03-17
36 | Screen Recording Functionality for Amazon Connect | Capability | In Progress | Hosting remaining | Shubhada/Pratyusha | 2023-04-30
37 | Amazon Connect custom CCP to answer calls and chat | Demo | In Progress | Yet to start | Shubhada/Pratyusha | 2023-03-31
38 | Redaction for Chat | Solution | In Progress | Yet to start | Shubhada/Pratyusha | 2023-04-10
39 | Chat widget availability on website depending upon agent availability and office hrs | Capability | In Progress | Yet to start | Shubhada/Rajiya | 2023-04-10
40 | Live Agent transfer option in Chat widget basis agent availability and office hrs | Capability | In Progress | Yet to start | Shubhada/Rajiya | 2023-04-10
41 | Demo setup in new Connect instance | Capability | In Progress | Configuration is in progress | Karan / Mohan | 2023-04-21
42 | IVR Modules creations and usage | Solution | Completed | Completed | Rajiya
43 | Customer whisper and agent whisper | Capability | Completed | completed | Rajiya
44 | Expand Network bot with Live Chat | Solution | Completed | Demo Available | Rajiya
45 | Automatic case creation and storing through IVR | Capability | Completed | Completed | Karan | 2023-06-01
46 | Scheduled callback with customer preferences | Solution | Completed | Demo Available | Rajiya
47 | Enable Amazon Connect Customer profiles with custom data | Capability | Completed | Completed | Rajiya
48 | Unum Bot | Demo | Completed | Demo Available | Shubhada
49 | Index Page for every solution | Solution | Completed | Demo Available | Shubhada
50 | Caller scheduled callback functionality | Capability | Completed | Demo Available | Karan | 2023-04-18
51 | setup in new Connect instance | Capability | In Progress | Configuration is in progress | Rajiya
52 | Connect CTR Data Export to DynamoDB | Capability | Completed | Demo Available | Karan | 2023-04-24
53 | Configure Single Sign-On for Amazon Connect Using Okta | Capability | Completed | Demo Available | Karan | 2023-06-12
54 | Real time Transcription Connect | Capability | Completed | Demo Available | Karan | 2023-05-03
55 | Updation of Evaluation Forms report in UI | Solution | In Progress | Configuration is in progress | Mohan/Pratyusha
56 | 3Shape voice and chat bot | Solution | Completed | Demo Available | Mohan/Pratyusha
57 | Enhancement of IVR Migration UI | Solution | Completed | configuration is in progress | Shubhada/Pratyusha | 2023-05-23
58 | ESOC Chat bot | Solution | Completed | Demo Available | Mohan/Pratyusha
58 | Connect Explorer Dashboard | Solution | Completed | Demo Available in Quicksight | Shubhada/Saurabh
59 | API's for Connect Explorer Dashboard | Solution | Completed |  | Saurabh
60 | compare 2 Amazon Connect instances either in same account or different account. | Solution | In Progress |  | Mathew/KARAN
61 | Foxtel UI | Solution | Completed | Demo available | Shubhada
62 | DoJ | Solution | Completed |  | Rajiya
63 | Instance Comparison UI | Solution | Completed | Demo Available | Shubhada
64 | GenAI Sumarization solution | Solution | Completed | Demo Available | Saurabh
65 | Compare two Connect Instances | Solution | Completed | Demo Available | Mohan/Shubhada
66 | Devops UI Enchancement | Solution | In Progress |  | Shubhada
65 | Telstra | Solution | Completed |  | Rajiya/Shubhada
66 | GenAI Sumarization solution UI | Solution | In Progress | Demo Available | Shubhada
67 | QnA Solution Using AWS Bedrock(Small PDF Upload) | Solution | Completed | Demo Available | Saurabh /Mohan
68 | DevOps Connect Queue,Quick connect, Routing profile, Security profile | Solution | Completed |  | Karan
69 | DevOps Lex | Solution | Completed |  | Karan
70 | QnA Solution Using AWS Bedrock(Large PDF Upload)- Embedding and Vectorization | Solution | Completed |  | Saurabh
71 | RAG Approach GenAI Serverless Solution using Kendra, Flan T5 FM and LangChain | Solution | Completed |  | Karan
72 | Foxtel PoC | Solution | Completed |  | Karan
73 | QnA Solution Using AWS Bedrock(CSV File) | Solution | Completed |  | Saurabh
74 | QnA Solution Using AWS Bedrock(Small PDF Upload) - OCR for Non-searchable PDF | Soution | Completed |  | Saurabh
75 | Agent Suggestion solution using Bedrock based on earlier Summay and solution provided | Solution | Completed |  | Saurabh
76 | Devops UI Enchancement & API Request Changes | Solution | Completed |  | Aniket
77 | Instance Comparison UI Revamped | Solution | Completed |  | Aniket
78 | Agent Contact Center (Gen AI Summarization UI Development) | Solution | Completed |  | Aniket / Seshu
79 | Network Bot (JavaScript) | Solution | Completed |  | Seshu
80 | Custom Chat Widget (Lex + Live Agent) | Solution | In Progress |  | Anket/Razia
81 | Embed Amazon CCP in React | Solution | Completed |  | Aniket
82 | Embed Amazon Agent Workspace in React | Solution | Completed |  | Aniket
83 | GenAI BOT for fallback intent |  | In Progress |  | Rajia/Saurabh
84 | Amazon Connect CCP in Microsoft teams | Solution | In Progress |  | Aniket
85 | SIP trunk between amazon connect and SBC on prem
86 | Embed Amazon CCP in JavaScript |  | In Progress |  | Seshu
87 | Revamp Document Chat UI | Solution | Completed |  | Aniket
88 | Revamp of Maze | Solution | Completed |  | Aniket
89 | Resource Tagging |  | Completed |  | Seshu
90 | Revamp Finops UI | Solution | Completed | New Screen or Dashboard Changes Expected | Aniket
91 | Email Generator using genAi ( Maze) |  | In Progress |  | Seshu
92 | Prudential Bot | Solution | Completed |  | Devi/Aniket
93 | EmailGenerator using genAI | Solution | Completed |  | Seshu
93 | Email Generator using genAi ( Maze UI) | Capability | Completed |  | Aniket
94 | Custom Softphone using React | Solution | In Progress | UX Optimization and Basic Features | Aniket
95 | AWS-RAG-UI | Solution | Completed |  | Aniket
96 | KMDB Solution(AWS RAG) | Solution | Completed |  | Saurabh
97 | Chatbot using AWS Bedrock(Titan model) | Solution | Completed |  | Saurabh
98 | FAISS-Vector-DB | Solution | Completed |  | Saurabh
99 | AWS-RAG-LEX-CHATBOT | Solution | In Progress | Need to migrate DynomoDB data in new account | Saurabh /Mohan
100 | AWS-Connectwise-Admin-Hub | Solution | In Progress |  | Aniket
101 | AWS-Aadhar-Auth-ChatBot | Solution | In Progress | Demo available for document upload with only PNG format | Rajiya/Aniket
103 | AWS-ConnectOps | Solution | Completed | Confluence of DevOps+FinOps+IC | Aniket
104 | Erie- AWS connect and Zendesk Integration | Demo | Completed | Demo Available | Mohan
105 | Resource Tagging - Amazon Connect | Solution | Completed |  | Seshu
106 | Cloud Formation for Amazon Lex | Solution | Completed |  | Seshu
107 | Cloud Formation for Lambda services | Solution | Completed |  | Seshu
108 | Configure granular access controls using Resource tags - Amazon Connect ( Lambda Development) | Solution | Completed |  | Seshu
109 | Configure granular access controls using Resource tags - Amazon Connect ( UI ) |  | Completed | In Progress | Seshu
110 | Voice-To-Chat | Solution | Completed | demo available | Rajiya/Aniket
111 | Cross account Lambda Calling | Capability | Completed | one account to other account call | Mohan
112 | Video-Call-Widget | Capability | Completed | Video Call Widget | Aniket
113 | Nielsen-survey | Solution | Completed | Demo Available | Rajiya
114 | London Transport Chatbot | Solution | Completed |  | Aniket/Devi
115 | RAG- Chatbots UI (multi-domain) | Solution | Completed |  | Aniket/Devi/Saurabh
116 | Evaluation Form UI Revamped | Solution | Completed |  | Aniket
117 | Auto ML Self learn bot(RAG-KMDB | Solution | Completed |  | Saurabh
Sr No | Task | Type | Status | Progress | Assigned To | Assigned On | Target to Complete | Idea From | Remarks
118 | Custom Lex BoT with UI and Complex UI component along with Live Chat deflection - Chatbot | Solution | Completed | 07/24 : Shared BOT and Payload with Aniket 07/25 : BoT Templates and testing 08/06 : Created lambda for connect LiveChat and Imported the Short Term data for Forecasting data 08/07 : Created cloud watch stream and added code logic in lex runtime lambda and making changes in lex bot and enabled the obfuscation for phone number and email and working on Form submit. 08/12 : Facing some challenges in Form submit and debugging 08/13 : Testing the Connect Agent, Supervisor functions and connect features like Cases, Customer Profile and Amazon Q and quick connect for voice and chat (voice is done)for chat cases were not creating checking CloudWatch logs and debugging .And done some modifications in custom lex bot and Checking the Form submit . 08/20 : Forms submit is done .. delection to live chat is pending need to test after making changes in UI | Rajiya/Mohan | 2024-07-18 | 2024-07-24 |  |  |  | Completed | In Progress
119 | Custom Lex BoT with UI and Complex UI component along with Live Chat deflection - UI | Solution | Completed |  | Aniket | 2024-07-18 | 2024-07-24
120 | Cloud Formation - Lambda | Capability | Completed |  | Saurabh | 2024-07-01 | 2024-07-26
121 | Audio to Text Transcription - replacement for AWS Transcribe , as it's costly service | Solution | Completed | 07/24 : Assembly AI , lambda development pending 07/25 : No work and progress 08/05 : Assembly.AI validated. | Saurabh | 2024-07-23 | 2024-07-26
122 | CF Session to Team | Training | Not Started | 07/25 : Training Pending | Saurabh | 2024-07-23 | 2024-07-24
123 | Agent Gamification | Solution | Enahnacements in Progress | 07/24 : Backend part is ready and API given to Seshu | Devi | 2024-07-01
124 | London Transport Demo - Voice IVR and Q integration | Solution | Completed | 07/24 : New IVR developed , resolving issues | Devi | 2024-07-11 | 2024-07-31
125 | Service Now Integration with PII redaction | Solution | Completed | 07/24 : IVR development and enable integration with Service Now 07/25 : Still work in progress 07/29 : Service Now is getting created | Mohan | 2024-07-22
126 | Python Code for Kinesis video stream | Solution | On HOLD | 07/25 : Still work in progress 07/29 : Devi is trying solution to work it out with Python rather Java code 08/12 : Tried to convert a sample mp3 file from s3 bucket using transcribe. And able to get the text transcribe file and stored it in the s3 bucket. 08/13 : Tried to convert audio using transcribe in realtime by passing the streams data. Facing issues debugging. 08/14,16: Able to convert the audio data to transcribe text. 08/19: Facing issues with the timeout of lambda (8sec) in amazon connect. The flow got stopped. 08/20: To avoid the timeout issue of lambda gone through the documentations of configuring lambda to kinesis streams. Implementation and testing pending. 08/21 : Added kinesis Trigger in the lambda code, Tested the flow ,even the call is more than 2 minutes the streams not having data. Just getting 17B or 20B file to s3 bucket. Debugging. 08/22 : Doing code changes in lambda in order to read all the records from the streams and checking whether the streams data is writing to file correctly or not. 08/23: Got to know that we need to call get media api inorder to get entire chunks from the streams. Hold that approach, Inorder to test the streams data , looked into the kinesis firehouse and direct data storage into the s3 bucket. | Mohan / Devi | 2024-07-22
127 | Dashboard and Readiness for AEGAS | Solution | Completed | 0/25 : Assigned and Explained | Rajiya | 2024-07-25 | 2024-07-26
128 | Admin Portal UI Development | Solution | On HOLD | 7/29 : Shared all APIs required for Development to Devi | Aniket
129 | Admin Portal API Development | Solution | In Progress | 7/29 : Yet to Start | Devi
130 | Realtime Transcript - UI | Solution | Completed |  | Aniket | 2024-07-29
131 | Data Lake Configuration for Amazon Connect | Solution | Completed | 08/05 : Explored Data Lake and Applied it to | Mohan | 2024-07-31 | 2024-08-02
132 | Responsible AI - What is It | Training | Completed |  | Saurabh | 2024-08-06
133 | amazon-connect-chat-translate | Solution | Completed | 08/06: Started exploring and understanding the git repo 08/7:- The github repo delpoyed manually using amplify console is not working need git account or need to try some another method | Mohan | 2024-08-06
144 | Demo - whitebread - to show capability of Contact lens | Demo | Completed |  | Harshil
145 | Demo - London transport - to show capability of amazon connect , quality management , GENAI solutions | Demo | Completed |  | Harshil
146 | Demo on Hypertonic | Demo | Partial completed |  | Harshil | next demo - last week of AUG
147 | CCI - PAID POC | Implementation | Completed |  | Harshil/Saurabh | waiting for environement access
148 | Assembly AI vs Amazon Transcribe PPT | Documentation | Completed | Lambda implementation and result validation completed | Saurabh
149 | Summarization solution migration | Solution | Completed | 12-08-2024 - Completed in old account | Saurabh
150 | RAG Chatbot solution | Solution | Completed | 13-08-2024 - Completed in old account | Saurabh
151 | Secure IVR | Solution | Completed | 08/20 : encrypting the customer inputed data is completed facing challenges with decrypting the data in lambda using packages | Mohan
152 | Whitbread Dual-Lang Chatbot | Solution | Completed |  | Aniket/Mohan/Rajiya | 2024-09-10
153 | PCI Compliance secure IVR | Capability | Completed |  | Mohan
154 | Enable real-time chat message streaming in Amazon Connect | Solution | Not Started |  | Seshu
155 | Social Media listener with Event Brideg and Twitter APIs Along with Amazon Connect Task | Solution | Not Started |  | Saurabh
156 | Hotel Booking Voice BOT | Capability | Completed |  | Rajia
157 | Hotel Booking Chat BOT | Capability | Completed |  | Rajia
158 | Hotel Booking Chat UI | Capability | Completed | Made the required changes needed for the lex response. | Seshu
159 | Hotel Booking Voice BoT and Chat BoT - Demo Recording | Capability | Completed | Chat & Voice Demo is recorded | Sanket
160 | Banking Voice BoT | Capability | Completed |  | Devi
161 | Banking Chat BoT | Capability | Completed |  | Devi
162 | Banking Chat UI | Capability | Completed | Made the required changes needed for the lex response. | Seshu
163 | Banking Voice BoT and Chat BoT - Demo Recording | Capability | Completed |  | Sanket
164 | Retail Voice BoT | Capability | Completed |  | Mohan
165 | Retail Chat BoT | Capability | Completed |  | Mohan
166 | Retail Chat UI | Capability | Completed | Made the required changes needed for the lex response. | Seshu
167 | Retail Voice BoT and Chat BoT - Demo Recording | Capability | Completed | Chat & Voice Demo is recorded | Sanket
168 | Insurance Voice BoT | Capability | Completed |  | Pratibha
169 | Insurance Chat BoT | Capability | Completed |  | Pratibha
170 | Insurance Chat UI | Capability | Completed | Made the required changes needed for the lex response. | Seshu
171 | Insurance Voice BoT and Chat BoT - Demo Recording | Capability | In progress | Insurance Chat Demo recording is completed | Sanket
172 | Post Call Analytics - Complete Solution - UI | Solution | Completed |  | Aniket
173 | Post Call Analytics - Complete Solution - Backend | Solution | Completed |  | Saurabh
174 | Include Chat Script Analysis with SmartAgent - UI for Supervisor | Solution | On HOLD |  | Aniket
175 | PreChat Form and Click to Call Feature in Custom Chat Widgets | Capability | Completed |  | Aniket
176 | Voice-To-Chat -cloudformation template | Solution | Completed | demo available | Seshu
177 | Text translation comparison (Google, AWS, LLM) | Documentation | Completed |  | Saurabh
177 | Text translation comparison (Google, AWS, LLM) | Documentation | Completed |  | Saurabh
179 | Agent Fatigue | Documentation | Completed |  | Sanket
180 | ITServicedesk | Solution |  |  | Rajiya
181 | Whitbread Custom ChatWidget (Language checking) |  | Completed |  | Aniket /Mohan
182 | Index Page UX Optimization (category bifurcation) |  | Completed |  | Aniket
183 | Retreiving metrices for all levels (Queues & Agent for all channels) - Info on Agent login, calls answered/abandoned and so on | Solution | Completed |  | Seshu
184 | Integrate Facebook Posts with AWS Connect | Solution | Not Started |  | Devi/Seshu
185 | Integrate Facebook Messenger with AWS Connect | Solution | Not Started |  | Devi/Seshu
186 | Integrate Instagram Posts with AWS Connect | Solution | In Progress | integration has been done, receiving messages for instagram. currently working on contact flow and lambda development | Devi/Seshu
187 | Retreiving metrices for historical outbound calls (Dialer initiated outbound calls and their status - answered/unanswered) | Solution | Completed |  | Seshu/Mohan
188 | Identification of Amazon Connect Queue by GEN AI - Reduce IVR branching with Gen AI (Voice calls should be directly routed to specific queue) | Capability | Completed |  | Saurabh/ Harshal
189 | Gen AI backed Gen AI FAQs Intent in Lex | Capability | On HOLD | Anthropic is required. Hence ON HOLD | Pratibha
190 | Enhancement of Amazon Connect Ops Solution | Solution | Completed | Dependencies on IVR call flow has been completed (LEX, Lambda and queues). Currently working on Modules. UI work needs to be done to showcase the dependencies in the URL | Mohan/Aniket
191 | Agent SmartDesk | Solution | Completed |  | Aniket/Saurabh
192 | LLM / Amazon Q Generate IVR flow | Solution | Not Started |  | Mohan
193 | Wickes Solution:Cost Optimized Gen AI usage along with Chatbot using Amazon Lex | Solution | Completed | Pratibha to connect with Saurabh for creating Knowledge Base files with CSV files 22-1-2024: Developing Wickes solution with Gen AI | Pratibha/Saurabh
194 | Research + POV on ALM (Audio Large Models) | Solution | Completed | 12/26 : Preparing POV on ALLM and details of ALLM 12/31 : Shared first draft with Siva for review and feedback | Sagar
195 | Customized Amazon Connect Consumption Calculator | Solution | In progress | TFN-DID, LEX and Recording details have been added | Sanket
196 | Single Slide on all Gen AI Solutions | Capability | Completed | Prepared slide and kept in solution folder in Teams | Sagar
197 | Explore email communication channel, Amazon Connect | Solution | In Progress | Email flow is configured. Mail auto response is pending | Sanket/Sagar/Harshal |  |  |  | Gen ai response varies sometimes.
198 | KT Document from Devi | Documentation | Completed |  | Devi/Sanket
199 | Explore Whats App channel from Amazon Connect | Solution | Not Started | awaiting for the business whatsapp phone number | Seshu
200 | Integrate Hotel Booking, Retail and Banking with Gen AI | Solution | Completed |  | Pratibha
201 | Develop POC for Audio LLM | Solution | In progress | Analysis using Audio LLM is completed. Integration with UI is pending | Saurabh/Aniket
202 | Gen AI for proactive communication | Solution | Not Started |  | Saurabh/Harshal
203 | AppFlow Connector between Lambda and Amazon Connect to populate Customer Profile Data | Solution | Not Started |  | Seshu
204 | Amazon Connect Different Applicatio Integrations , ServiceNow, Salesforce , UI Application etc | Capability | Not Started |  | Sagar
205 | Templatized Amazon Lex enablement with Gen AI - Intent Idetification Lambda - Intent Idetification & Utterances Matching, Prompting | Solution | Completed |  | Pratibha/ Sanket
206 | Enhance Amazon Lex Testing Tools - UI and enhance functionality of it | Offering | Not Started |  | Aniket/Harshal
207 | Agent SmartDesk - Customer Sentiment Live, Agent Compliance (Greeting , Name ), Agent Response (Positive, Empathetic , Comprehensive), Interaction Reason Predections, | Solution | In progress | Aniket has configured the Basic look & feel, item placement approved. Saurabh to work on API and provide the details to Aniket | Aniket/Saurabh
208 | Quality Co-Pilot - Query CTR Data with Amazon Gen AI and gather intellegence on Call IDs for longer hold time, Calls IDs with longer call duration, Calls Ids with top queue and calls | Solution | Not Started |  | Saurabh
209 | Slides for Dyanamic Queuing and routing with Gen AI | Solution | Completed | Prepared slide and kept in solution folder in Teams | Sagar
210 | Cloud front for chat BOTs and Smart Agent desk | Offering | Completed |  | Aniket
211 | Chat History in SmartAgent Desk & Custom Chat Widiget solution post chat deflected to Agent | Solution | Completed |  | Mohan/Aniket
212 | Mutlilinguil BoT Enhacement to avoid translation for proper noun | Solution | Not Started |  | Mohan/Harshal
213 | Customer Profile within SmartAgent | Solution | In progress | Trying to fit in existing application via maximize/minimize approach | Aniket
214 | Email channel in Smart Desk | Solution | Not Started |  | Aniket/Harshal
215 | Maximize/Minimize & Draggable Custom Chatbot (IT Helpdesk) | Solution | Completed | working on max/min and draggable part | Aniket | 2025-01-21
216 | Audio LLM | Solution | Completed |  | Aniket/Saurabh
217 | Responsive IT Helpdesk Chatbot | Solution | Completed |  | Aniket
218 | Email Flow Demo recording | Solution | Completed |  | harshal/Sanket
219 | Agent to Agent chat | Solution | In progress |  | Aniket/Venkat
220

## Wickes_GenAI_Solution
Wickes Solution Resources
Lambda | WIcks_API
Wicks_Lambda
| Wicks_Response_Template | (used when creating vector db using lambda)
AWS Instance | Demo2
Lex Bot | Wickes_Bot
S3 Bucket to store logs | rag-vector-db-storage
S3 file path | Wicks_LLM_CSVs/
Amazon Bedrock Knowledgebase | Wickes_KB2
Datasource for Vector DB creation(S3 Bucket) | rag-vector-db-storage
Wicks_Docs/

## Templatization_solution
Wickes Solution Resources
Lambda | Templatized_Lambda
AWS Instance | Demo2
Lex Bot | Templatized_Bot
S3 Bucket to store logs | rag-vector-db-storage
S3 file path to store logs | Templatization_csv/
Amazon Bedrock Knowledgebase | KB2_Templatization
Datasource for Vector DB creation(S3 Bucket) | templatization-bucket
folder1/
DynamoDB Table | Retail_Customer_DB

## Meta Integration
Service | Step Description | Services Link
Meta Webhooks | To trigger events from meta when messages are received | Meta for Developers
API GateWay | To Create a public endpoint for meta to send data | MetaAPI
Lambda Function | To handle webhook verification ( GET ) and process messages (POST) | amazonConnectWithInstagram
EC2 (type: t3.micro) | Used to facilitate development, testing, and managing meta for developer account | connectWithInstagram
Meta for Developers | to set up meta for developers account | Social technologies ¦ Meta for Developers

## Audio LLM Solution
Lambda
Audio-Transcribe-and-Analysis-using-AssemblyAI
S3
Bucket Name : | rag-vector-db-storage
Folder : | Audio_Files
Assembly_AI_Analysis_DB
UI URL | https://d3fzajeshhktgv.cloudfront.net/
http://allm-demo-ui.s3-website-us-east-1.amazonaws.com/

## Email Call Flow
Instance | Demo 1
Domain | tcsawsdemo.email.connect.aws
Demo1 email ID | demo1@tcsawsdemo.email.connect.aws
S3 Storage | awsconnect-emaildemo
AWS Connect Flow | Email Call Flow
Email Queue | Email_Queue_Test
Routing Profile | email_test
Lambda (extracting email body details) | Email_test_flow
SQS queue | case-events-queue
Rule | case-events-to-sqs-queue
Lambda (extracting case details) | SQS_Case_Event
hosted zone created in route53
helpdesk@tcsawsdemo.email.connect.aws

## Customer Call Logger Metrics
URL | Description | Lambda Name
CustomerCallMetricsLogger | allow you to dynamically fetch agent IDs and other relevant details associated with outbound calls made to customer phone numbers. | CustomerCallMetricsLogger

## Metrices for all levels
URL | Description | Lambda Name
Real Time Lambda | This lambda fetches real time metrics for both agent and queues | metricdata-for-all-levels
Historicals Lambda | This lambda fetches historical metrics metrics for both agent and queues | historicalMetricsLambda

## Post Call Analytics
Info | Post Call Analytics transcipt based (txt,zip,wav file type)
UI URL | Generative AI Summarization
Login | John / John@123
UI Code S3 Bucket | s3://aniket-ui-codes/latest_codes/
Lambda Details | Description
Transcript-Summary-Analysis-From-Wav-File | This Lambda is responsible for analysing and conversion of audio wav file to text transcript
Transcript-File-Upload-Summarization-Solution | This Lambda is responsible uploading text/wav file from UI
GenAI-Transcript-Summary-Based-On-ID | This Lambda is responsible for getting all transcript summary details based on ID
GenAI-Get-Summary-Details-from-DynamoDB | This Lambda is responsible for getting all transcript summary details based on Date range
GenAI-Fetch-File-Names-transcript-solution | This Lambda is responsible for getting all transcript file name details
GenAI-Agent-Compliance-Transcript-solution | This Lambda is responsible for getting agent compliance status
Call-Transcript-Summary-Overview-Details | This Lambda is responsible for getting last 10 records
GenAI-Transcript-Summary-Analysis-Save-To-DynamoDB | This Lambda is responsible for transcript analysis and save it to dynamoDB table

## Queue Detection using GenAI
Lambda | Description
Queue_selection_FallbackIntent | This lambda is hooked to lex bot | This lambda is merged with the second lambda (Queue-selection-using-GenAI)
Queue-selection-using-GenAI | This Lambda is responsible for detection of queue based on user query and pass response to Lex lambda for further processing
Lex | User_query_genai
Connect flow | queue_genai
tcsawsdemo

## Agent Smartdesk
Info | Application with realtime message translation from any customer language to english and vice versa, along with canned message and agent assist faq section to help customer faster and efficient
UI URL - Instance 1 | https://d2zuo6s7gho5tp.cloudfront.net
UI URL - Instance 2 | https://d3hpur7tuj24t0.cloudfront.net/
Agent Login | Agent/Agent@1234
Supervisor Login | Supervisor/Supervisor@1234
Amazon Connect Login | Instance 1 login Id/pwd
UI Code S3 Bucket | s3://aniket-ui-codes/latest_codes/
Lambda Details : | Description
Agent-Assist-RAG-VectorDB | This lambda is responsible for creation of knowledge base vector DB
Language_Detection_And_Translation_Lambda | This lambda is responsible for language detection and translation using AWS Translator service
Agent-Assist-Language-Detection-And-Translation-Using-LLM | This lambda is responsible for language detection and translation using LLM
Agent-Assist-RAG-Response-DB | This lambda is responsible for getting response from knowledge Base

## InsuranceBot
Insurance Chatbot Resources |  | Insurance Voice Bot Resources
Lambda | Insurance_OTP | Lambda | Insurance_Voice_Flow
Insurance_Lex_Lambda
Insurance_Auxillary
Connect Flows | Insurance_Flow2 | Connect Flows | Insurance_VoiceBOT_Demo
| Insurance_Testing |  | Insurance_Auxiliary
Insurance_CreditCardDetails
AWS Instance | Demo2 |  | PCI_AgentUI
Amazon Pinpoint Project | Banking | Amazon Pinpoint Project | Banking
DynamoDB Table: | Insurance_Customer_Details | DynamoDB Table: | Insurance_Customer_Details
Lex Bot | Insurance_Bot | Lex Bot | Insurance_Voice_Bot
UI URL | https://d267rqf97mlodt.cloudfront.net
Lambda
Amazon Pinpoint Project
Banking
DynamoDB Table:
Insurance_Customer_Details
Lex Bot
Insurance_Voice_Bot

## Hotel Booking
Index
| For Chat Bot |  | Voice Flow
Amazon Lex | HotelBooking-Bot |  | HotelBooking-Voice
Connect Instance | tcsawsdemo2 |  | tcsawsdemo2
IVR Flow | Hotel-Booking-Chat |  | HotelBooking-Voice
Lambda Main function | HotelBooking-Func | to check the details of the customer from dynamo db.. triggered from lex
UI calling Lambda | HotelBooking-LexAPI | Lex chat bot to be called from UI
Dynamo DB | TCSAWSBUCE_CommonDatabase
API Gateway | HotelBooking (txw345zlvf)
URL | http://hotel-booking-bot-ui.s3-website-us-east-1.amazonaws.com/
https://d1678p2vamjixd.cloudfront.net

## Banking
Banking Chat Solution: | Lambda: BankingChat Banking-LexAPI | Lex: Banking_Chat_Bot | Connect: Banking_Chat_Flow | Amazon Pinpoint: Banking | DynamoDB: TCSAWSBUCE_CommonDatabase | AWS Instance: Demo 2 | URL: http://banking-bot-ui.s3-website-us-east-1.amazonaws.com/
Banking Voice Solution: | Lambda: Banking | Lex: Banking_Call_Bot | Connect: Banking_VoiceBOT_Demo | Amazon Pinpoint: Banking | DynamoDB: TCSAWSBUCE_CommonDatabase | AWS Instance: Demo 2 | https://d1mdqnfcu9xifa.cloudfront.net

## ITServicedesk
Index
Amazon Lex | ITservicedesk
Connect Instance | tcsawsdemo
IVR Flow | Custumlexbot-Liveagent
Lambda Main function | ITServicedeskbot-func
UI calling Lambda | ITservicedesk-lex
Dynamo DB | ITServicedesk-ticket
API Gateway | https://fblcv87lnd.execute-api.us-east-1.amazonaws.com/dev/
URL | http://it-helpdesk-custom-chatbot.s3-website-us-east-1.amazonaws.com/
https://d3q1ctbcrgqai1.cloudfront.net

## IVR Recording(Post call Survey)
First flow | Survey Flow | Description - Customer gets connected to agent
Second Flow | Survey Questions | Description - After agents end the call, customer is asked two feedback questions and one free input.
Lex | Survey_Bot | Description - Used to get free input from user
Conclusion | Our end goal was to record ivr recording (audio) like prompts played, agent and customer interactions. But it is observed that when the agent is disconnected and customer is transferred using set disconnect flow to second flow that time set recording block throws error, because it only works for inbound flow. So, we were not able to record (audio) of the interactions happening in second flow.
Detailed Explanation | IVR Recording(Post call Survey).docx

## Q and Bedrock intent
QinConnect | Bedrock AgentIntent.docx
Bedrock Intent | “QinConnect” for automated replies to customer.docx

## Whitbread-Multi-Lang
Index
For Chat Bot |  | For Voice
Amazon Lex | WB-ChatBot-NEW | wb-multilang-voicebot
Connect Instance | tcsawsdemo | tcsawsdemo
IVR Flow | WBCustumlexbot-Liveagent | wb_multilang | wb_agentworkspace- agent workspace flow
Lambda Main function | WB-LexBot
UI calling Lambda | WB-LexBot
API Gateway | https://ocipmj9wo4.execute-api.us-east-1.amazonaws.com/dev/
URL | http://whitbread-custom-chat-widget.s3-website-us-east-1.amazonaws.com/
https://doo87zdb7u3kh.cloudfront.net

## Retail Bot
Index
AWS Instance | Demo2
Ivr Flow | retail-bot-flow | Voice call flow
| retail-bot-chat-flow | chat call flow
| retail-bot-start-callback | call back option from UI
| retailbot-AgentWorkspace | Agent custom workspace
lex bot | Retail-Bot | voice chat bot
lambda function | retail-bot | to check the details of the customer from dynamo db.. triggered from lex
| retail-lexchatbot | Lex chat bot to be called from UI
Api | retailbot-UI-connect | Api to inovke chat bot
Dynamo Db | TCSAWSBUCE_CommonDatabase | #Data base with primary id phone number and details regarding last purchase of the customer and Customer details
S3 | retail-bot-ui | bucketNAme
URL | https://dqdelx5hzeibs.cloudfront.net
http://retail-bot-ui.s3-website-us-east-1.amazonaws.com/

## PCI Compliance secure IVR
Index
Connect IVR | Sample Live Chat
QuickConnect | creditCardDetails |  | IVR flow | CustomerCreditCardDetails
| #connected to BasicQueue |  |  | #Flow where agent goes on hold and customer enter credit card details
Agent UI FLow | PCI_AgentUI |  |  | #In amazon connect console we upload the public key to get the key id which can be used later
S3 | s3://mohan-codes/PCI Compliance Data/ |  |  | #During get customer input block where credit card details are entered we use the key id which was created above and the certificate
| #public key , private key and certificate are stored |  |  | #using secure-ivr-lambda to to store the encrypted Data in Secure_encrypted_data Dynamo DB
Lambda | secure-ivr-lambda
Dynamo DB | Secure_encrypted_data
Lambda To decrypt | DecryptCustomerInputV2
| Sample Lambda Event JSON | s3://mohan-codes/PCI Compliance Data/LambdaTestEvent.json

## Custom Chat Widget
Summary | Custom AWS Chat Widget which supports LexBot as well as Live Agent Chat (developed using React.JS and Amazon ChatJs Library for Live Chat)
UI URL | Custom AWS Chatbot UI (custom-lexbot-via-lambda.s3-website-us-east-1.amazonaws.com)
UI Deployed S3 | custom-lexbot-via-lambda
Lambda

## Auto ML Self learn bot(RAG-KMDB
Lambda
GenAI-Lex-Transcript-Knowledge-Base-1
GenAI-Lex-Transcript-Knowledge-Base-2
GenAI-lex-transcript-Knowledge-base-response
GenAI-Lex-Transcript-Knowledge-Base-CSV-File-Details-API
S3 Bucket
lex-transcript-storage
Link
http://qna-chatbot-ui.s3-website-us-east-1.amazonaws.com/

## RAG Chatbot(Multi-Domain)
UI Link | RAG Chatbots (rag-chatbots-ui.s3-website-us-east-1.amazonaws.com)
Banking Bot | Lambda Banking_RAG_Calling BankingBot --> UI LEX BankingBotRag
Finance Bot | Lambda Finance_RAG_Calling FinanceBot --> UI LEX FinanceBot
Life Science Bot | Lambda LifeScience_Rag_Calling LifeScienceBot LEX LifeScienceBot
Insurance Bot | Lambda Insurance_Rag_Calling InsuranceBot LEX InsuranceBot

## London Transport Chatbot
UI Link | London Transport (london-transport-chatbot.s3-website-us-east-1.amazonaws.com)
IVR Flow | Amazon connect Instance 2: https://tcsawsdemo2.my.connect.aws LondonTransport
Lambda Functions | NewAccount: LondonTransport Enabled Bedrock Anthropic Claude Model and wrote code for genai integration Old Account: LondonTransport Did Cross Lambda Configurations to use bedrock services . | Cross Lambda Configurations New Account to Old Account [To use Bedrock Models] NEW ACCOUNT CONFIGURATIONS: 1. In RoleAdd an inline policy to invoke lambda (same lambda arn) 2. In trusted relationships, specify the lambda arn of other account lambda's role.[Role ARN] OLD ACCOUNT CONFIGURATIONS: 1. Specify the role arn of new account lambda function in an inline policy.
Lex Bot | Old Account LondonTransport Created few intents with questions and then configured lambda function in the fallback intent to trigger gen ai .
S3 Bucket | AmazonQ Bucket details for pdf file : amazon-connect-1f4a87d8f81d S3 Bucket Details for CSV in new account: csv-data-storage LondonTransport/LondonTransport_Faq.csv We stored the pdf in 2 places, one for bedrock integration and other for amazon Q
Amazon Q Domain Integration | Go to the Amazon Connect instance2 and there we can have amazon q option. Do follow the below steps -> Add integration -> Select S3 as a source -> Specify Integration Name -> Give Amazon Q S3 bucket : amazon-connect-1f4a87d8f81d After integrating this Amazon Q with S3 bucket details then We need to configure Amazon Q in the IVR flow as well in the Amazon Q Connect Block.

## KinesisRealtimeTranscription
Amazon Connect Flow: | Indian Lang Flow: Enable Media streaming block in the start of the flow and Stop media streaming block at the end of the flow before disconnect block.
Amazon Lambda | KVSTrigger: Which picks stream arn of the kinesis vidoe streams once the call is initiated in the connect flow and pass that stream arn to the actual processing lambda. Kenesis_Video_to_audioFile: Which gets triggered by the kvstrigger lambda and using get media api picks the stream and store that in webm in a s3 bucket. Process the webm file using ffmpeg and store the mp3 file in s3 bucket.
S3 | kenesis-stream-audio-file
Kinesis Data Streams | realtime-transcription-test

## AgentGamification
Lambda | AgentDataRetrieval: Which will fetch data from the amazon connect AgentGamificationUI: fetch from dynamo db and return to ui

## Nielsen-survey
Index
AWS LEX | NielsenSurvey-Bot
Lambda | Survey-Feedback-Func
Pinpoint | Nielsen-survey
Connect Instance | tcsawsdemo
Connect IVR | Nielsen-Survey
DynamoDB | 1.Nielsen-Survey , 2. Nielsen-surveydata
UI URL | http://nielsen-survey-chatwidget.s3-website-us-east-1.amazonaws.com/
http://xyz-survey-widget.s3-website-us-east-1.amazonaws.com/

## AWS-Connectwise-Admin-Hub
Custom AWS Connect Admin Platform
UI URL | http://connectwise-admin-hub.s3-website-us-east-1.amazonaws.com/

## Video Call Widget
Solution shows the capability of video call feature for agent
UI URL | http://vc-widget-demo.s3-website-us-east-1.amazonaws.com/

## CrossAccountLambdaCall
Index
Lambda | US Account | Cross-account-lambda-testing
| India Account | Cross-account-role-testing

## CloudFormation for Lex & Lambda
Index
Creating Amazon lex & Lamba with cloudFormation
Bot Name
BookTripWithCFN
LambdaName
mystackforlambdaexample
CloudFormation Stacks
mystackforlambdaexample1
MyStackForLex

## AWS-RAG-LEX-CHATBOT
AWS Services | Name

## KMDB Solution(AWS-RAG)
AWS Service | Name
S3 Bucket | document-data-storage
URL | http://aws-rag-ui.s3-website-us-east-1.amazonaws.com/
Lambda : | Description
GenAI-Knowledge-Base-1 | This lambda is responsible for generating issue and solution from transcript data and save it in s3 bucket(CSV file)
GenAI-Knowledge-Base-2 | This lambda is responsible for generation og knowledge base with CSV file stored in s3 containing issue and solution
GenAI-Knowledge-Base-CSV-Read-API | This lambda is responsible for getting all the issue nd solution details by reading csv file from S3
GenAI-Knowledge-Base-Response | This lambda is responsible for getting response from knowledge base

## Email Generator
Index
Lambda Ref | description
email-generator | This Lambda function processes incoming API requests to generate dropdown options or create email content using AWS Bedrock’s text generation capabilities. It supports dynamic email generation based on user-provided parameters such as email type, language, and word count.

## Chatbot using AWS Bedrock-Titan
Services | Name
EC2 | aws-cloud9-Ec2-for-layer-creation-0736dbc79c294812b53fb27f5f5c8e64

## FAISS-Vector-DB
AWS Service | Name
S3 Bucket | document-data-storage
Lambda | VectorDB_Langchain_CSVread

## AWS-Aadhar-Auth-ChatBot
Index | This solution is used for to upload Aadhar document in the chat bot and verify that aadhar.
AWS Console | New Account
Lex Bot | Document-upload-bot
Lambda | Images-Rekognition
S3 | documentupload-chat
URL | http://aadhar-auth-chatbot.s3-website-us-east-1.amazonaws.com/

## Voice-To-Chat
This solution is designed to redirect customers having long wait time on call with agent to switch to chat channel.
Voice -To- Chat- Transfer(Using SNS)
Index
Aws Console | Old Account
AWS connect Instance | tcsawsdemo
AWS connect IVR | voice to chat-flow
Queue | Basic Queue
S3 | chat-widget-html
Lambda | Voice_to_chat_func
Pinpoint
UI URL | http://voice-to-chat-widget.s3-website-us-east-1.amazonaws.com/
Voice -To- Chat- Transfer(NEW Using Pinpoint)
AWS connect Instance | tcsawsdemo
AWS connect IVR | voice to chat-Channel deflection
Lambda | Voice-to-chat-transfer
S3 | voice-to-chat-widget-new
cloudfront | EVYUKSVUCOQXH
url | From lambda signed url
Connect Modules | voice to chat-Module (This can be used for Cloudformation Template )

## ErieDemo
Index
US Account
AWS Connect |  |  | Lambda
Instance1 (tcsawsdemo)-For Testing |  |  | Erie-Zendesk-TicketCreation | For Creating tickect if call ends on self service
Chat Bot | ContactFLow | Erie-ChatBot | Erie-lexconnect | For IVR and Chat responsese which is triggered from lex
IVR | ContactFLow | Erie-MainFlow | Erie-voice-id-authentication | For VOice ID check for IVR
|  |  | Erie-callTranscript-store | For Storing Transcript of lex in Dynamo db
Instance2 (tcsawsdemo)-For DEMO
Chat Bot | ContactFLow | Erie-ChatBot | DynamoDB
IVR | ContactFLow | Erie-MainFlow | Erie-CustomerData | Stores Customers Phone NUmbers to which OTP should send
|  |  | Erie-TranscriptStore | Stores Transcript
AWS Lex |  |  | Erie-voice-authentication | Stores VOice ids
Erie-lexChatBot | For Chat Purpose
Erie-lexbot | For IVR

## Prudential-ChatBot
Index | This solution is used to answer the FAQ's related to HR Domain(prudential). It contains GEN AI Approach.
UI Link | http://prudential-bot.s3-website-us-east-1.amazonaws.com/
Solution 1: Chatbot + Bedrock | AWS Lambda : Prudential_Bot - To integrate lex with lambda and then with UI using function url. [ New Account ] CrossLambda_Prudential - To enable cross lambda permissions within 2 accounts. [ Old Account ] Pridential_Faq - Main file which invoke bedrock model to answer user queries. [ New Account ] AWS Lex : Prudential_Bot - Contains intents with sample questions, welcome,ending and fallback intent which calls CrossLambda_Prudential . [ Old Account ] Amazon Bedrock : Model - Anthropic Claude v2 [ New Account ] Amazon S3 : Bucket_Details : faq-csv-storage/prudential_faq/ [ New Account ] WebsiteURL : UI Link - http://prudential-bot.s3-website-us-east-1.amazonaws.com/
Solution 2: Chatbot + Bedrock Agent and Knowledgebase (Paused As the agent responses are too late) | [New Account - Oregon Region] AWS Lambda : PrudentialBot_KB-Agent - Integrated with Bedrock Agent. AWS Lex : PrudentialAgent Amazon Bedrock : Knowledge Base : Prudential_Knowledge_Base Agent : Prudential_Agent Amazon S3 : Bucket_Details : faq-csv-storage/prudential_faq/
Solution 3: Chatbot + RAG Approach | New Account : AWS Lambda : Prudential_RAG_Implementation AWS Lex : Prudential_Bot_RAG Amazon Bedrock : S3 :

## NetworkBot(JavaScript)
Index
url | http://test-demo923.s3-website-us-east-1.amazonaws.com/

## customerOutboundLambda
customerOutboundLambda | This lambda makes an outbound call to the customer which fetches from the csv file stored in s3 bucket

## Amazon Connect Tagging
Index
Assigning a metadata to the resources in Amazon connect in the form of tags
Lambda
connectTag

## AmazonCCP-Javascript
URL | http://amazonccp-javascript.s3-website-us-east-1.amazonaws.com/

## Resource Tagging full stack
Index
Configure granular access controls using Resource tags - Amazon Connect ( UI )
Configure granular access controls using Resource tags - Amazon Connect ( Lambda Development)
UI Link
http://connect-ui-for-tags.s3-website-us-east-1.amazonaws.com/
Lambda References
connect_tagging
listTagsConnect
revamp of connectTag
s3Bucket
s3 code base

## DevOps Connect Queue,QC,RP,SP
Index
CodeCommit Repo | Devops-Connect-SCM-SB-BKP
Rule | codepipeline-Devops-main-125151-rule |  | triggers on new changes in codecommit
CodePipeline Pipeline | Devops-Connect-Pipeline-SB-BKP
Pipeline Action Lambda | Devops-Connect-Publish-Miscel-BKP |  | #lambda which triggers when pipeline runs
DynamoDB ARN Table | Devops-Connect-SB-ARN-Table
Connect Instances | tcsawsdemo
tcs-salesforce-connect
tcsawsdemo components | SBDevQueue(Queue)
SBQC(Quick Connect)
SBRP(Routing Profile)
SBSP(Security Profile)
tcs-salesforce-connect components | SBDevQueue(Queue)
SBQC(Quick Connect)
SBRP(Routing Profile)
SBSP(Security Profile)
The New devops additions checks the dependencies of the json like module, lex bots and lambda, we can add or deleete or map the instances
amazon_connect_instance_management- lambda
Part of Connect DevOps Solution, Lambda interacts with dynamo DB to change the dev,uat,production evns or add new env
https://841c5aajwa.execute-api.us-east-1.amazonaws.com/dev/ apis connect with lambda
checkDependenciesOfJson - lambda
checks the dependencies of ivr json like lambda, lex and modules
https://z3ucm8fei7.execute-api.us-east-1.amazonaws.com/dev/ apis connect with lambda
DevOps-Envt-Table | DynamoDB table | #for instance configuratuion

## Foxtel PoC
Index
Connect Instance | tcsawsbuconnectworkflows | (Region - ap-southeast-2)
Contact Flow | Foxtel CC
Foxtel CC Chat
Authentication Lambda | FoxtelCC-AgeVerify
Authentication DynamoDB | FoxtelCC-DDB
IVR Lex | SupportBot
SupportBotChat
Lex Lambda | FoxtelSupportBotFunction
FoxtelSupportBotFunctionChat
Authentication Lex | FoxtelAuthBot
SNS Topic | FoxtelCC
Api gateway(livechat) api | StartChatContact (p6rpj9mbs2)
Api lambda | startChatContactAPIforFoxtel-StartChatLambda-9wVIGiUWhDHA
UI Link | http://foxtelsolution.s3-website-us-east-1.amazonaws.com/

## RAG Approach GenAI Kendra Soln
Index
Lambda | GenAiUCAppLambda
Sagemaker Endpoint | jumpstart-dft-hf-text2text-flan-t5-xl | (required, but deleted for cost purposes)
Kendra index | GenAiUC | (required, but deleted for cost purposes)
Kendra Knowledge base S3 | genaiuc-kendra-s3-ds-docs

## DevOps Lex
Index
Login | john
pwd | John@123
event bridge rule | codepipeline-Devops-master-114874-rule | triggers on new changes in codecommit
CodeCommit Repo | Devops-Lex-SCM-BKP
CodePipeline Pipeline | Devops-Lex-Pipeline-BKP
Pipeline S3 | devops-lex-scm-bkp-s3
Pipeline Lambda | Devops-Lex-PublishLexZip-BKP | #lambda which triggers when pipeline runs
Lex Bots Used For Testing | HealthFAQBot-DevOps-Dev
HealthFAQBot-DevOps-Prod
IAM Custom Role | AWSServiceRoleForLexV2Bots_CustomRole
UI Lambda | Devops-Lex-UI | #lambda connects the UI
UI S3 | devops-lex-ui-files
UI Audit DynamoDB | Devops-Lex-AuditTrail

## Foxtel
url : | http://foxtelsolution.s3-website-us-east-1.amazonaws.com/

## Custom Softphone using React
Gist | Custom Softphone made using Amazon Connect Streams library and React.Js
UI Link (Cloudfront) | https://d2lwlt6rgbs5yi.cloudfront.net/
S3 Deployed Link | http://custom-aws-ccp.s3-website-us-east-1.amazonaws.com/

## GenAIsummarization
url: | http://generative-summarization.s3-website-us-east-1.amazonaws.com/
new url | http://gen-ai-summary-ui.s3-website-us-east-1.amazonaws.com/
Lambda : | Call-transcript-summary
connect-ctr-data-store-direct

## Instance Comparison
new url | http://instance-comparison.s3-website-us-east-1.amazonaws.com/
url | http://instance-comparison-web.s3-website-us-east-1.amazonaws.com/

## Telstra
Index
NBN Appointment
url | http://telstraweb.s3-website-us-east-1.amazonaws.com/
Lex Bot |  | Telstra-Bot
AWS Connect Alias |  | tcsawsdemo
Connect Flow |  | Telstra-voice
DID |  | Any free DID can be used and mapped to the Contact flow
Queues |  | Basic Queue
Modem Troubleshooting
Lex Bot |  | Telstra-Bot
AWS Connect Alias |  | tcsawsdemo
Connect Flow |  | Telstra-Flow
DID |  | Any free DID can be used and mapped to the Contact flow
Queues |  | Basic Queue

## FInops Dashboard
url: | http://finopsboard.s3-website-us-east-1.amazonaws.com/
new url | http://finops-newui.s3-website-us-east-1.amazonaws.com/

## Compare Instances
Index
# will compare 2 connect instances in same or different region we need instance id and regions
Lambda |  | Compare-Connect-Instances
Lambda layer |  | CompareTwoInstances
Api |  | compareInstances
website |  | Instance Comparison (instance-comparison-web.s3-website-us-east-1.amazonaws.com)
new url |  | Instance Comparison (instance-comparison.s3-website-us-east-1.amazonaws.com)

## DoJ
index
DOJ - Chat BOT - Visa appointment cases
AWS Connect Alias | tcsawsdemo
Connect Flow | DoJ-Flow
DID | Any free DID can be used and mapped to the Contact flow
Queues | Basic Queue
Lex Bot | DoJ-lexchatbot
Web page chat url | http://doj-ui.s3-website-us-east-1.amazonaws.com

## LondonTransport
IVR Flow | Amazon connect Instance 2: https://tcsawsdemo2.my.connect.aws LondonTransport
Lambda Functions | NewAccount: LondonTransport Enabled Bedrock Anthropic Claude Model and wrote code for genai integration Old Account: LondonTransport Did Cross Lambda Configurations to use bedrock services . | Cross Lambda Configurations New Account to Old Account [To use Bedrock Models] NEW ACCOUNT CONFIGURATIONS: 1. In RoleAdd an inline policy to invoke lambda (same lambda arn) 2. In trusted relationships, specify the lambda arn of other account lambda's role.[Role ARN] OLD ACCOUNT CONFIGURATIONS: 1. Specify the role arn of new account lambda function in an inline policy.
Lex Bot | Old Account LondonTransport Created few intents with questions and then configured lambda function in the fallback intent to trigger gen ai .
S3 Bucket | We stored the pdf in 2 places, one for bedrock integration and other for amazon Q AmazonQ Bucket details for pdf file : S3 Bucket Details for CSV in new account: csv-data-storage LondonTransport/LondonTransport_Faq.csv
Amazon Q Domain Integration | Go to the Amazon Connect instance2 and there we can have amazon q option. Do follow the below steps -> Add integration -> Select S3 as a source - till bucket name -> Specify Integration Name -> add kms key as amazon-connect-tcsawsdemo -> Give Amazon Q S3 bucket : amazon-connect-1f4a87d8f81d After integrating this Amazon Q with S3 bucket details then We need to configure Amazon Q in the IVR flow as well in the Amazon Q Connect Block.

## Call Summarization solution
Summarization Solution Details
Sr No | Service | Service Name | Description
1 | lambda | connect-ctr-data-store-direct | This lambda save CTR data along with call transcript and summary in DynamoD Table
2 | lambda | Call-transcript-summary | This lambda provides call summary data and transcript using L2L call from connect-ctr-data-store-direct
UI URL | http://gen-ai-summary-table.s3-website-us-east-1.amazonaws.com/

## QnA pdf solution using Bedrock
Bucket: | chatbot-document-files
Lambda : | Q-and-A-predictor

## Enable Amazon Connect Customer
index
Aws Connect Instance | tcsawsdemo2
Flow Name

## Custom CCP
Description: | To implement amazon connect ccp in custom UI.
url | https://d2lwlt6rgbs5yi.cloudfront.net/

## Screen Recording functionality
Description: | It is functionality to implement screen recording of agent chat application.
s3 bucket name: shubhada-ui-codes

## Whatsapp Virtual Assistance
Description : | It is a functionality in which we have integrated lex and connect to whatsapp.

## Facebook Virtual Assistance
Description: | It is solution in which we integrate facebook messenger with amazon connect and lex and implement live chat functionality in that.

## IndexPage
Description | It is a index page of all the solutions direct links.
Url | http://indexsolution.s3-website-us-east-1.amazonaws.com
https://dkuzlb1awqmw4.cloudfront.net
Index

## Create Amazon connect flow API
Index | Simple API which we can create connect flow
Connect Instance |  | tcsawsdemo
Lambda |  | Devops-Connect-Create_Contact_FlowAPI

## IVR Migration details
Index
s3 website hosting link |  | : | http://ivr-migration-ui.s3-website-us-east-1.amazonaws.com
new ui url |  |  | http://ivr-migration-updated-ui.s3-website-us-east-1.amazonaws.com/
Contact flow | dev[tcsawsdemo]
prod[tcs-salesforce-connect]
dev-bkp[tcsawsdemo]
prod-bkp[tcs-salesforce-connect]
S3 | devops-connect-data
devops-connect-data-bkp
devops-connect-ui-gc-bucket
Lambda | Devops-Connect-CallDescribeContactFlowApi
Devops-Connect-UpdateContactFlowJson
Devops-Connect-PublishContactFlowJson
Devops-Connect-CallDescribeContactFlowApi-BKP
Devops-Connect-UpdateContactFlowJson-BKP
Devops-Connect-PublishContactFlowJson-BKP
Devops-Connect-RevertChanges
Devops-Connect-Create_Contact_FlowAPI
Devops-Connect-CheckQueues
Devops-Connect-CheckLambdas
Devops-Connect-ShowDynamoDB
Devops-Connect-UpdateDynamoDB
Devops-Connect-UpdateContactFlowJson-GHJN
Devops-Connect-UI-GC
Code Commit Repo | Devops-Connect-SCM
Devops-Connect-SCM-BKP
Code Pipeline | Devops-Connect-Pipeline
Devops-Connect-Pipeline-BKP
Api Gateway Api's | https://ohl5an2en1.execute-api.us-east-1.amazonaws.com/dev/getddbdata
https://ohl5an2en1.execute-api.us-east-1.amazonaws.com/dev/updateddbdata
https://ohl5an2en1.execute-api.us-east-1.amazonaws.com/dev/startpipeline
DynamoDB | Devops-Connect-Data
Devops-Connect-AuditTrail
Devops-Connect-UserAuditTrail
UI | React App
Ec2 Instance for Jenkins | i-0d91c7faa67214c6a
Descripton: |  | Enchacement of look and feel of UI.
UI Full Code Bucket Name(React) - |  | ivr-full-code

## ESOC chat bot
Index
s3 url | EOSC (eosc-ui.s3-website-us-east-1.amazonaws.com)
Api Gateway | ESOC-chat-Api
Lambda | ESOC-chat-integrationWithUI
| EOSC-lexConnect | #tiggers on fulfilment on some intents to fetch or create data in dynamo db
lex | ESOC-bot
Dynamodb | EOSC-TicketsData | #stores and fetches ticket data

## Connect SSO with Okta
Index
Okta Account | username | gupta.karan3@tcs.com | [Trial acc valid for 30 days only]
| password | Tc$@wsbu108
Connect Instance | tcsawsconnectworkflows
IAM Policies | okta_federation_policy
okta_cli_policy
IAM User | okta_cli_user
Relay URL | https://us-east-1.console.aws.amazon.com/connect/federate/34ca734e-b28e-4e2e-b91c-85fa43ec264d
IAM Identity provider | Okta_Connect_Admin
IAM Role | Okta_Role

## Automatic case creation
Index
Connect Instance | tcsawsdemo2
Module | Connect-Case
Contact Flow | Case-Flow
Phone No | +1 401-655-6460
Case Template | OrderFeedbackCase
Customer Profile | 917889693790
Lex | Connect-Case-Bot

## 3Shape
Index
| chat |  |  | voice
s3 url | http://3shape-ui.s3-website-us-east-1.amazonaws.com/
Api Gateway | StartChatContact
Lambda | startChatContactAPI2-StartChatLambda-Zxw8PpIHeHB5 |  | #to start connect flow from front end used unum lambda... need to change contactg flow id in code
| 3Shape_passwordReset |  | #to check the data present in dynamo db | 3Shape_passwordReset
lex | 3ShapeBot |  |  | 3Shape-voicebot2 | #account number intent is not getting triggered so using 2nd bot for account number
3Shape-Voicebot
post call survey
Dynamodb | 3Shape_CustomerData |  |  | 3Shape_CustomerData
| feedback | #feedback storing
connectFlow | 3Shape |  |  | 3Shape-Voice
| customersurvey | #transfers to the flow for feedback
New instance
connectFlow | 3Shape-livetransfer
| postcall survey | #transfers to the flow for feedback

## Evaluation forms in UI
Index
s3 buckect | http://evaluationform-ui.s3-website-us-east-1.amazonaws.com/ | #Ui link
| amazon-connect-form-evaluations/connect/tcsawsdemo/ContactEvaluations | #path to s3 where the contact evaluations are stored
Api Gateway | AgentEvaluationForms
Lambda | UpdateEvaluationForm | # To get the form data to UI, to update the data
| Update-s3csvfile-on-AgentEvaluationofForm | # will update the dynamo db on submitiing evaluation form
Dynamodb | EvaluationForms
Updated UI URL | http://eval-form-ui-updated.s3-website-us-east-1.amazonaws.com/
Sr no | Description | Phase | Status | ETA to complete
1 | Rule Engine to trigger Alert to Supervisor | 1 | Completed
2 | Evulation is Done automatically | 1 | Completed
3 | UI is devleoped for Agent and Supervisor to view and Supervsior can edit machine response | 1 | Completed
4 | To test evaluation form API | 2 | Pending
5 | To create dashboard on no of evaluation eligble and how many are completed | 2 | under Progress
6 | Auto Assignment of Supervisor once rule is triggered | 2 | Pending
7 | evaluation is done by which supervisor | 3 | Dropped
8 | Dashboard for overall score of customer sentiment / week / month | 3 | Pending
9 | Agent can raise dispute on evlaution feedback and send to supervisor for discuss | 3
10 | Supervisor can get Agent wise evulation ID option | 3

## Real time Transcription Connect
Index
Contact Flow | Realtime-Transcriptionx[any cf where contact lens is enabled]
Kinesis data stream | Realtime-Transcription
Lambda | Realtime-Transcriptiony
DynamoDB | Realtime-Transcription-DDB-2.0
Kinesis Instance Association Cmd | aws connect associate-instance-storage-config --instance-id bd16d991-11c8-4d1e-9900-edd5ed4a9b21 --resource-type REAL_TIME_CONTACT_ANALYSIS_SEGMENTS --storage-config 'StorageType=KINESIS_STREAM,KinesisStreamConfig={StreamArn=arn:aws:kinesis:us-east-1:768637739934:stream/Realtime-Transcription}'
Experiment Lambdas associated | Realtime-Transcriptionx
Realtime-Transcription2x
Realtime-Transcription
Realtime-Transcription2
Experiment DynamoDB | Realtime-Transcriptionx-DDB
Experiment Contact Flow | Realtime-Transcription

## Connect CTR Data Export to DDB
Index
Connect Instance | tcsawsdemo
Kinesis delivery stream | PUT-S3-BIVpi
S3 Bucket | connect-ctr-data-store
Lambda | connect-ctr-data-store
DynamoDB | connect-ctr-data-store-ddb
Kinesis data stream | connect-ctr-data-store
Lambda | connect-ctr-data-store-direct
DynamoDB | connect-ctr-data-store-direct-ddb

## Dynamic Prompts And WaitTime
Index
New instance
Contact Flow | DynamicPrompts
Number | +1 267-846-5033 |  |  | Module | QueueWaittime | #used in main flow
Lambda | DynamicPrompts | need to add lambda function in connect
| Get-Queue-waitTime | converts seconds to minutes
Dynamo DB | FlowPrompts |  | #Fetches the dynamic prompts using flow name
Item - DynamicPrompts, key-contact ID

## Agent To Agent Call transfer
Index
QuickConnects | Agent David
David- David@123
You Can assign Quick Connects to Any Queue after you are in call you can see the contact after you recive the call
Supervisor
Hafiz- Hafiz@123

## Network Bot
Index
AWS Connect Instance | tcsawsdemo
Lex primary Bot | primarybot
Lex Secondary Bots | HealthFAQBot,CovidFAQBot,ClaimFAQBot
Lex Lambda | Network-bot-func
S3 Url | URL - http://conciergelex.s3-website-us-east-1.amazonaws.com/
S3 BucketName | conciergelex
API Gateway | https://kehqi0b20d.execute-api.us-east-1.amazonaws.com/dev/
Network bot using connect contact flow transfer
Connect primary flow | Network Bot -Flow
Connect secondary flows | Networkclaim-secondary bot Networkcovid-secondary bot NetworkHealth-secondary bot
lambda | Testing_lex_PrimaryBot
API Gateway | http://unumbot.s3-website-us-east-1.amazonaws.com/
Queues | ClaimQueue,HealthQueue,CovidQueue
Live chat
Inorder to start the connect flow we need to change the connect flow id in the lambda | startChatContactAPI2-StartChatLambda-Zxw8PpIHeHB5
Description | it is a solution in which we have a primary bot which comprised of many secondary bots .

## Fraud Detection
Index | Amazon connect can be used to managed the fraud detector service to find the fraudulent / high risk callers whather the customer is legit /Investigate/Fraud
Aws connect Alias | tcsawsdemo
Connect Flow | Fraud detection
DID | Any free DID can be used and mapped to the Contact flow
Queues | Basic Queue,fraudqueue
DynamoDB | frauddetection
Lambda | Fraud-detection

## Unum Bot
Index Page
Unum Bot : Live Chat via Amazon Connect along with Amazon Lex integration. Agent Handoff with Context transfer
Amazon Connect Instance
Amazon Lex Name : | UnumBot
Amazon Contact Flow Name: | UnumFlow
Post Chat Survey Lex name : | customersurvey
Post Chat Survey Flow name: | post call survey
Survey dynamo db : | feedback
WebPage URL : | http://unumbot.s3-website-us-east-1.amazonaws.com/
Demo Index Page URL : | ??????
Description: | It is solution to implement live chat functionality with amazon connect and interactive messaging in custom chat widget.

## Caller scheduled callback fn
Index
Ivr flow | Caller scheduled callback flow
Lex bot | CallerScheduledCallbackBot
Lex Lambda | CallerScheduledCallbackBotLambda
Dynamodb | CallerScheduledCallbackData
Eventbridge Rule | callbackRule
EB Target Lambda | Start_outbound_voice_contactLambda
Callback Ivr flow | callback-flow
DID | Any free DID can be used and mapped to the Contact flow

## Evaluation Form
index
Evaluation Form | Name-NICE Evaluation Form | #Have Enabled Scoring and automated the form using Rules
Email will be trigged when Authentication rule is trigged |  | #need to enable the contact lens in connect flow
| Rule Name:- sending Email | #will send the email to to the email id of the agent selected on configuring the rule
# you can evaluate the call in contact search
New Instance
Evaluation Form | Name-Agent Performance Check EF | #Have Enabled Scoring and automated the form using Rules
Rules | rules have been create for each question which can be automated
| APC-EF_Rule-{section}-{questionNo} | #rules have been created under this format
Login Page
Username | John
Pwd | John@123

## Network Bot
URL - http://conciergelex.s3-website-us-east-1.amazonaws.com/

## Agent Assist suggestion box
Agent Assist with suggestion box and automation of chat response with pre configured response messages
Dynamo Db table Name: |  | AgentInfo
Description: | In this we have multiple messages of different categories stored in dynamodb which can assist agent to reply in meaningful and effective manner.
code in s3 bucket name: shubhada-ui-codes

## search display functionality
Keywords based multilingual search display functionality using Amazon opensearch and amazon translation
Index
AWS OpenSearch Domain Name : |  |  | searchfaqs
Lambada Names : |  | 1. Retailfaqs |  | 2. Searchfaqs
DynamoDb Table name : |  | RetailFAQs
Description: | It is a solution in which we have search different faqs and we get result and we can translate that t different languages.

## Chatbot transfer to Live Agent
Index
Contact Flow | SparcTestingChat
Lambda | SparcCheckAutheChat
Dynamo DB | SparcCheckAutheDB
Lex | SparcBotForTestingChat
Lex Lambda | SparcBotForTestingLambdaChat
Lex Log group | LexBotTestingLGChat
CF SFDC Case Lambda | serverlessrepo-AmazonConnectSalesforce-sfInvokeAPI-AZseHciLk7aD
Queue | Basic Queue
DID | Any free DID can be used and mapped to the Contact flow
SFDC URL | https://tcsrig.my.salesforce.com/
Lambda | SparcSFChatbotHistoryChat
SparcSFPutChatbotHistorySFChat
Dynamo DB | SparcSFChatbotHistoryDbChat
Prerequisite | Testing number entry should be added accordingly in dynamodb table comparing previous entries for proper order details retrieval
Testing number contact should be created in salesforce for successful case creation
UI | http://reebokweb.s3-website-us-east-1.amazonaws.com/
Description: | It is usecase in which we have integrated ivr flow with custom chat widget with live chat transfer functionality.

## Outbound Campaign
Index
contact flow | Outbound-Callback
Pinpoint | connectoutbound
connect Outbound campaigns | Outbound-Campaign
Connect Instance | tcsawsdemo

## Multilingual Bot
Index
Multi Lingual Chat Bot
Lex bot name: | FAMLI_ChatBot
Website Link | https://vt-surveywebsite.s3.ap-south-1.amazonaws.com/PFML_Website/PfmlWebsiteChatbot.html
Lambda | famliValidations
Description: | It is a chatbot in which we can talk or ask to bot in multiple languages.
Multi Lingual Chat Bot |  | #new
Api Gateway | MultiLangChatBot
s3 | multi-lang-chatbot
http://multi-lang-chatbot.s3-website-us-east-1.amazonaws.com
lambda | Multilingual-chat-bot-with-lex
Lex bot name: | MazeBot

## Chat Virtual Assistance
Index
Amazon Lex | IndustrialAllianceBot | (Lex V2)
Website Link | https://d137jyz4ldctww.cloudfront.net/
Lambda | IndustrialAllianceBotLambda- lex bot trigger lambda |  | Ticketincident-customerdetailsfunc
Dynamo Db table | incident table and call id table
Description | It is a solution in which we have configured a lex bot in UI to have chat from uI with le capabilities.

## Postcall Survey
Index |  | New Instance
Aws connect instance | tcsawsdemo
Contact flow | postcall survey | postcall survey
Lambda | customerfeedback
DynamoDB | feedback
Aws Lex | customersurvey

## Amazon Connect Dashboards
Index
Quicksight | feedback analysis
data set (This data taken from dynamo db) | feedback

## Lex Dashboards
Index
Quicksight 1 | cumminsuclexlambdalogcsv analysis | Quicksight 2 | lexpasswordresetbot
quicksight data set | cumminsuclexlambdalogcsv | quicksight data set | 10
Glue | cumminsuclexlambdalogcsv | Glue | passwordreset-database
Athena database | cumminsucbot | Athena database | passwordreset-database
Lex | CumminsUCBot | lex | PasswordResetBot
Lambda(In athena we get unformated data so i used this func to bring into proper data columns) | quicksightdatastructure | Lambda(In athena we get unformated data so i used this func to bring into proper data columns) | quicksightdatastructure2
S3 | lexcumminsucbot | S3 | lexpasswordresetbot
a

## Email and SMS Campaign Maze
index
Service | Name | Description
cloudfront | https://d3gtckpoeib4ve.cloudfront.net/ | If we use this link for Email or SMS first we need to create a project before creating segment
S3 | mace-site | uploded site
| mace-tcs | csv files stored using presigned url
Mumbai-region
Api | mace
resource-
| uploadsegement | need to upload customer data in csv file | #Segment refers to csv file of customer data
| createcampaign | triggers a Email or SMS using selected Segment | #campaign refers to a event it can be SMS or Email
| getprojects | Shows the created Campaigns and Segements in project-in lambda function event changes for showing Campaign and segments function is same
#we need to select SMS or Email while creating campaign
Lambda | mace_pinpoint | lambda for get projects api , if inevent intent changes i.e getSegments and getCampaigns
| generatingPresignedUrlForFileUpload | uploads csv file in s3
| creatingSegmentOnS3Trigger | on s3 updation segment is created
| mace-segments-campaigns | creates campaign

## Realtime Transcript & Translate
Index
Custom CCP URL | https://d1b675abe2nxos.cloudfront.net/agentAssist.html
Contact flow | Y-kvsStreamingFlow
Agent whisper | y_agentWhisperKvsStreamingFlow
Lambda | arn:aws:lambda:us-east-1:768637739934:function:CustomCCP-with-Realtime-SpeechA-kvsConsumerTrigger-WQCX7AXD5GYJ
arn:aws:lambda:us-east-1:768637739934:function:CustomCCP-with-Realtime-SpeechA-initContactDetails-TYYXJIITCWJU
Queue | Basic Queue
DID | Any free DID can be used and mapped to the Contact flow

## Authentication via Voice ID
Index
Contact flow | 1 NMAC Demo Voice ID
Lambda | Nissan-NMAC-Demo
Dynamo DB | Connect-TCS-NOAM-Users
Lex | Nissan-Demo
Nissan-Demo-2
Lex Lambda | Nissan-Lex-With-Voice_Id
Queue | Basic Queue
DID | Any free DID can be used and mapped to the Contact flow

## Voice Virtual Assistance
Index
Contact flow | 1 NMAC Demo Voice ID
Lambda | Nissan-NMAC-Demo
Dynamo DB | Connect-TCS-NOAM-Users
Lex | Nissan-Demo
Nissan-Demo-2
Lex Lambda | Nissan-Lex-With-Voice_Id
Queue | Basic Queue
DID | Any free DID can be used and mapped to the Contact flow

## Connect integration with SFDC
Index
Contact Flow | Sparc-ReebokUC
Lambda | SparcCheckAuthe
Dynamo DB | SparcCheckAutheDB
Lex | Sparc-ReebokUCBot
Lex Lambda | Sparc-ReebokUCBotLambda
Lex Log group | AwsLexbotLogs
CF SFDC Case Lambda | serverlessrepo-AmazonConnectSalesforce-sfInvokeAPI-AZseHciLk7aD
Queue | Basic Queue
DID | Any free DID can be used and mapped to the Contact flow
SFDC URL | https://tcsrig.my.salesforce.com/

## Inbound IVR Calling
Index
Contact Flow | Sparc-ReebokUC
Lambda | SparcCheckAuthe
Dynamo DB | SparcCheckAutheDB
Lex | Sparc-ReebokUCBot
Lex Lambda | Sparc-ReebokUCBotLambda
Lex Log group | AwsLexbotLogs
CF SFDC Case Lambda | serverlessrepo-AmazonConnectSalesforce-sfInvokeAPI-AZseHciLk7aD
Queue | Basic Queue
DID | Any free DID can be used and mapped to the Contact flow
SFDC URL | https://tcsrig.my.salesforce.com/

## Lex integration with Alexa
Index
Alexa skill | Find Doctor and Book Appointment
Lambda | ask-python36-fact-finddoctor-12f3405a9e21
Dynamo DB | _Doctor_
Dynamo DB | _Appointment_
Alexa skill | book appointment with a doctor
Lambda | ask-python36-fact-0e35e523f99f
Dynamo DB | Doctor
Dynamo DB | Appointment
Alexa skill's URL | https://developer.amazon.com/

## Lex integration with Genesys
Index
Lex | BillComplaintBot
Lambda | GenesysCloudUseCase3Lambda
Dynamo DB | GenesysCloudUseCaseAutheDB
Lex | HotelBookingBot
Lambda | GenesysCloudUseCase2Lambda
Dynamo DB | GenesysCloudUseCaseAutheDB
Dynamo DB | GenesysCloudUseCase2HotelSearchDB
Lex | PasswordResetBot
Lambda | GenesysCloudUseCase1Lambda
Dynamo DB | GenesysCloudUseCaseAutheDB

## C&Sf- transcript and pii redact
Index
Contact Flow | SparcTesting
Lambda | SparcCheckAuthe
Dynamo DB | SparcCheckAutheDB
Lex | SparcBotForTesting
Lex Lambda | SparcBotForTestingLambda
Lex Log group | LexBotTestingLG
CF SFDC Case Lambda | serverlessrepo-AmazonConnectSalesforce-sfInvokeAPI-AZseHciLk7aD
Queue | Basic Queue
DID | Any free DID can be used and mapped to the Contact flow
SFDC URL | https://tcsrig.my.salesforce.com/
Lambda | SparcSFChatbotHistory
SparcSFPutChatbotHistorySF
Dynamo DB | SparcSFChatbotHistoryDb
Prerequisite | Testing number entry should be added accordingly in dynamodb table comparing previous entries for proper order details retrieval
Testing number contact should be created in salesforce for successful case creation

## Bot Supervised training
Index
S3 bucket ui code | bot-training-ui
CF distribution | https://dluqzur8b6cjw.cloudfront.net
Dynamo DB | LexMissedUtterances
Lambda | updateLexBotV2
Get_Lex_Utterances_From_DynamoDB
lexquicksightdashboard
lexquicksightdashboard2
lexquicksightdashboard3
API Gateway | Bot_Training_API
Lex | TCSAWSBU
Lex | MasterBot
Lex Lambda | MasterBotLambda

## New Connect Instance
Index
Connect Instance Alias |  | tcsawsdemo2
Call Recording stored |  | 1f4a87d8f81d/connect/tcsawsdemo2/CallRecordings
S3 |  | amazon-connect-1f4a87d8f81d/connect/tcsawsdemo2
Contact Flow |  | BokingOrder_Flow
Modules |  | QueueWaittime,Caller scheduled callback flow,callback-flow
Queues |  | Basic Queue,Bookingorderqueue
Callback contact Flow |  | Callback_flow
Quickconnect |  | AgentQC,BookingorderQC
Rules and Evalutionform |  | FormName-Agent Performance Check EF... RulesName--APC-EF-Rule-{sectionNo}-{QuestionNO} |  | Email and Event bridge will be triggered when APC-EF-Rule-1-1
Email is not coming to tcs mail... event bridge is getting trigged.... Event bridge Name APC-EF-
Features Completed
1.Contact Lens
2.Callback
3.Quickconnect
4.Queuewaittime
5.Rules and Evalution form
6.Call Barge
7.Voice ID
8.Cases creation
9.Agent whispher |  | Lambda- connectpostcallsurveyfunc, Dynama Db -Agent_whisper
10.customer profiles |  | For custom data i have used sample data which uploaded in s3 - lexpasswordresetbot, file: CustomerProfileSampleData
| Sr no | Solution Description | Phase | Owner | Status
| 1 | Inbound IVR Calling | 1 | Rajiya | Completed
| 2 | Voice ID authenthication | 1 | Rajiya | Completed
| 3 | Voice BOT | 1 | Karan | Completed
| 4 | Chat BOT | 1 | Rajiya | Completed
| 5 | Mulitlingual Chat BOT | 1 | Mohan | Completed
| 6 | POST call Survery | 1 | Rajiya | Completed
| 7 | Real time Transcription | 1 | Karan | Completed
| 8 | Estimated wait time in queue if agent unavailable to take calls | 1 | Mohan | Completed
| 9 | Automatic case creation and storing through IVR | 1 | Karan | Completed
| 10 | Scheduled callback with customer preferences | 1 | Rajiya/Karan/Mohan | Completed
| 11 | Omnichannel outbound campaigns | 1 | Rajiya | Dropped
| 12 | Task management | 1 | Karan | Completed
| 13 | Rules engine - to trigger evulation | 1 | Mohan | Completed
| 14 | Evaluation forms and contact scoring | 1 | Mohan | Completed
Phase2
| 1 | Amazon Connect Wisdom | 2 | Karan | Completed
| 2 | Dashbaord configuration | 2 | Rajiya | Completed
| 3 | customer profile | 2 | Rajiya/Karan/Mohan | Completed
| 4 | agent workspace | 2 | Rajiya/Karan/Mohan | Completed
| 5 | Contact forecasting | 2 | Mohan | onHold
| 6 | Capacity planning | 2 | Mohan | onHold
| 7 | Real-time conversational analytics with sentiment analysis | 2 | Rajiya | Completed
| 8 | Call recording | 2 | Rajiya | Completed
| 9 | CTR data - In Data DYNAMO DB | 2 | Karan | Completed
| 10 | Connect Chat - 3shape with agent handoff | 2 | Mohan | Completed
phase3
| 1 | Configure Single Sign-On for Amazon Connect Using Okta | 3 | Karan | Completed
| 2 | call recording archival | 3
| 3 | Live chat - with language transaltion | 3
| 4 | Generative AI | 3

## Ctr data export to ddb new ins
Index
Connect Instance | tcsawsdemo2
Kinesis data stream | tcsaws2-ctr-data-store
Lambda | tcsaws2-ctr-data-store
DynamoDB | connect-tcsaws2-ctr-data-store

## Connect Wisdom new instance
Index
Connect Instance | tcsawsdemo2
S3 | tcsawsdemo2-connect-wisdom-s3kb
Lambda | ConnectWisdomS3KB
For Reference | TcsAwsbuWisdom wisdom domain
assistantArn: 'arn:aws:wisdom:us-east-1:768637739934:assistant/914a4311-0113-4a00-9d66-4e0403aa3876'
assistantId: '914a4311-0113-4a00-9d66-4e0403aa3876'
S3KB knowledge base name
knowledgeBaseArn: 'arn:aws:wisdom:us-east-1:768637739934:knowledge-base/9b232660-c1fc-4981-b853-40e45ae6460a'
knowledgeBaseId: '9b232660-c1fc-4981-b853-40e45ae6460a'
assistantAssociationArn: 'arn:aws:wisdom:us-east-1:768637739934:association/914a4311-0113-4a00-9d66-4e0403aa3876/fd092112-3ea6-4eb1-a53c-f32206605a54'
assistantAssociationId: 'fd092112-3ea6-4eb1-a53c-f32206605a54', 'assistantId': '914a4311-0113-4a00-9d66-4e0403aa3876'
IntegrationAssociationId: 'c068f288-0bfd-4697-a5c5-e913e24ac543'
IntegrationAssociationArn: 'arn:aws:connect:us-east-1:768637739934:instance/d75ee48a-a107-44fd-a22d-3f77fc7bdd38/integration-association/c068f288-0bfd-4697-a5c5-e913e24ac543'
[for assistant]
IntegrationAssociationId: 'edcc2560-22d9-49e4-baa7-f0d25c2f6850'
IntegrationAssociationArn: 'arn:aws:connect:us-east-1:768637739934:instance/d75ee48a-a107-44fd-a22d-3f77fc7bdd38/integration-association/edcc2560-22d9-49e4-baa7-f0d25c2f6850'
[for knowledgebase]
Knowledge Base | S3KB
Wisdom Domain | TcsAwsbuWisdom

## Task management new instance
Index
Connect Instance | tcsawsdemo2
Module | Connect-Case
Contact Flow | Case-Flow
Phone No | +1 401-655-6460
Case Template | OrderFeedbackCase
Customer Profile | 917889693790
Lex | Connect-Case-Bot
Task Template | OrderFeedbackTask
Queue | SupervisorQueue
Routing Profile | SupervisorRP
Task Contact Flow | CallSupervisor

## Rt Transcription new instance
Index
Contact Flow | Case-Flow[any cf where contact lens is enabled]
Kinesis data stream | Realtime-Transcription-tcsawsdemo2
Lambda | Rt-Transcription-tcsawsdemo2
DynamoDB | Rt-Transcription-ddb-tcsawsdemo2
Connect Instance | tcsawsdemo2

## Bot supervised Testing
Index
S3 bucket ui code | bot-training-ui
CF distribution | https://dluqzur8b6cjw.cloudfront.net
Api | AutomationBotTestingToolAPI
Lambda | UploadingFileToS3ThroughLambda
LexAutomatedTestingUtteranceTool
ReadFromS3
S3 bucket | lex--automated--utterance--testing
Lex | V2-Connect_TCS_NOAM_Sanbox
Lex Lambda | Lambda-Connect-TCS-NOAM-Sandbox
Dynamodb | ChatHistoryTable

## Amazon Connect CICD
Index
s3 website hosting link | http://cicdlatest.s3-website-us-east-1.amazonaws.com
Contact flow | dev[tcsawsdemo]
prod-bkp[tcs-salesforce-connect]
dev[tcsawsdemo]
prod-bkp[tcs-salesforce-connect]
S3 | devops-connect-data
devops-connect-data-bkp
devops-connect-ui-gc-bucket
Lambda | Devops-Connect-CallDescribeContactFlowApi
Devops-Connect-UpdateContactFlowJson
Devops-Connect-PublishContactFlowJson
Devops-Connect-CallDescribeContactFlowApi-BKP
Devops-Connect-UpdateContactFlowJson-BKP
Devops-Connect-PublishContactFlowJson-BKP
Devops-Connect-RevertChanges
Devops-Connect-Create_Contact_FlowAPI
Devops-Connect-CheckQueues
Devops-Connect-CheckLambdas
Devops-Connect-ShowDynamoDB
Devops-Connect-UpdateDynamoDB
Devops-Connect-UpdateContactFlowJson-GHJN
Devops-Connect-UI-GC
Code Commit Repo | Devops-Connect-SCM
Devops-Connect-SCM-BKP
Code Pipeline | Devops-Connect-Pipeline
Devops-Connect-Pipeline-BKP
Api Gateway Api's | https://ohl5an2en1.execute-api.us-east-1.amazonaws.com/dev/getddbdata
https://ohl5an2en1.execute-api.us-east-1.amazonaws.com/dev/updateddbdata
https://ohl5an2en1.execute-api.us-east-1.amazonaws.com/dev/startpipeline
DynamoDB | Devops-Connect-Data
Devops-Connect-AuditTrail
Devops-Connect-UserAuditTrail
UI | React App
Ec2 Instance for Jenkins | i-0d91c7faa67214c6a
|  | Sr No | Description | Phase | Status | ETA to complete
|  | 1 | Automated Contact flow changes through UI from Lower environment to higher environment | 1 | completed | completed
|  | 2 | Audit logs to track changes | 1 | completed | completed
|  | 3 | Revert changes through UI to revert promotion | 1 | completed | completed
|  | 4 | Maintaing central ARN table to maintian all changes | 1 | completed | completed
|  | 5 | Remove dependency of filling Contact flow ID manually of both environment | 1 | completed | completed
|  | 6 | To show drop down for flow name | 1 | completed | completed
|  | 7 | Flow ID should be non editable | 1 | completed | completed
|  | 8 | Promotion Commit message needs to be populated via UI | 1 | completed | completed
|  | 9 | Audit -- filtering mechanism , Promotion , OBJECT NAME and type ( changes done was ) | 1 | completed | completed
|  | 10 | In JSON file -- Download / VIEW option in UI | 1 | completed | completed
|  | 11 | Cross region automation to be tested | 1 | completed | completed
|  | 12 | Instead of Dev flow id and Prod flow id - ( Source and destination In name) | 2 | underprogress | 28/9
| Phase wise date in ppt | 13 | Console level updation of instance for lex, lambda | 2 | underprogress | 28/9
| Mention in phase wise slide - phase 1 - approach code commit and code pipeline | 14 | Automated Lex bot changes through UI from Lower environment to higher environment | 2 | underprogress | 28/9
|  | 15 | To extened solution from 2 environment to multi-environment scneario | 2 | underprogress | 28/9
|  | 16 |  | 2 | underprogress | 28/9
|  | 17 | Lambda Automation | 3 | pending
|  | 18 | Dyanamo DB Automation | 3 | pending
|  | 19 | Batch process for everyday automation | 3 | pending
|  | 20 | Report - This week , BAR graph , dashbaord , changes per week | 3 | pending
|  | 21 | Track changes in contact flow as versions | 3 | pending
|  | 22 | Think on charge mechanism | 3 | pending
|  | 23 | Creating cloud formation template | 3 | pending
|  | Sr No | Description | Phase | Status | ETA to complete
Connect Flow
|  | 1 | 80 Perce | 1 | completed | completed
|  | 2 | Audit logs to track changes | 1 | completed | completed
|  | 3 | Revert changes through UI to revert promotion | 1 | completed | completed
|  | 4 | Maintaing central ARN table to maintian all changes | 1 | completed | completed
|  | 5 | Remove dependency of filling Contact flow ID manually of both environment | 1 | completed | completed
|  | 6 | To show drop down for flow name | 1 | completed | completed
|  | 7 | Flow ID should be non editable | 1 | completed | completed
|  | 8 | Promotion Commit message needs to be populated via UI | 1 | completed | completed
|  | 9 | Audit -- filtering mechanism , Promotion , OBJECT NAME and type ( changes done was ) | 1 | completed | completed
|  | 10 | In JSON file -- Download / VIEW option in UI | 1 | completed | completed
|  | 11 | Cross region automation to be tested | 1 | completed | completed
|  | 12 | Instead of Dev flow id and Prod flow id - ( Source and destination In name) | 2 | underprogress | 28/9
|  | 13 | Console level updation of instance for lex, lambda | 2 | underprogress | 28/9
|  | 14 | Automated Lex bot changes through UI from Lower environment to higher environment | 2 | underprogress | 28/9
|  | 15 | To extened solution from 2 environment to multi-environment scneario | 2 | underprogress | 28/9
|  | 16 |  | 2 | underprogress | 28/9
|  | 17 | Lambda Automation | 3 | pending
|  | 18 | Dyanamo DB Automation | 3 | pending
|  | 19 | Batch process for everyday automation | 3 | pending
|  | 20 | Report - This week , BAR graph , dashbaord , changes per week | 3 | pending
|  | 21 | Track changes in contact flow as versions | 3 | pending
|  | 22 | Think on charge mechanism | 3 | pending
|  | 23 | Creating cloud formation template | 3 | pending

## Connect-Ops
Confluence of FinOps, DevOps and Instance Comparison
UI URL | http://aws-connect-ops.s3-website-us-east-1.amazonaws.com/
https://d3jr6pvtkgal66.cloudfront.net
Latest Changes URL | http://connect-ops-latest.s3-website-us-east-1.amazonaws.com/